## Executive Summary
PROJECT ALPHA — Client Portal Modernization
Project Proposal & Status Report
PROJECT DETAILS |  |  |  | KEY METRICS
Client | Northwind Financial Group |  |  | Total budget (incl. contingency) |  | 796345
Executive sponsor | Dana Whitfield, CFO |  |  | Spent to date |  | 370100
Project manager | Jordan Lee |  |  | Remaining budget |  | 426245
Proposal date | 2026-10-15 |  |  | % of budget used |  | 46.47%
Status date | 2027-03-31 |  |  | Overall % complete |  | 46.87%
Planned start | 2026-11-02 |  |  | Milestones complete |  | 2 of 7
Planned finish | 2027-07-30 |  |  | Overdue phases |  | 1
Total duration | 271 |  |  | Project health |  | At Risk
SCOPE & OBJECTIVES
1. | Replace the legacy client portal with a modern web app that lets clients view, edit, and approve financial documents in the browser.
2. | Keep sensitive client files inside the application — no download-edit-reupload loop and no third-party processing.
3. | Cut average approval turnaround from 6 business days to 2 by Q3 2027.
4. | Launch to 1,200 client users with full training and a 2-week hypercare period.
BUDGET SNAPSHOT BY CATEGORY |  |  |  | APPROVALS
Category | Budget ($) | Actual ($) | % Spent | Role | Name | Decision
Labor | 584600 | 294850 | 50.44% | Executive sponsor | Dana Whitfield | Approved
Software & Licensing | 77850 | 63250 | 81.25% | IT security | Kim Nguyen | Approved
Infrastructure | 18000 | 12000 | 66.67% | Finance | Priya Shah | Pending
Training & Change | 18000 | 0 | 0%
Professional Services | 25500 | 0 | 0%
Fictional sample project created for product demo videos. Names, figures, and dates are illustrative.
Color key: blue text = input · black = formula · green = linked from another sheet · yellow fill = key assumption
Note on C10: Key assumption: the 'as of' date for every status calculation in the workbook. Change it to move the project forward in time.

## Cost Breakdown
Cost Breakdown
Project Alpha — line-item budget, actuals to date, and monthly spend plan
Contingency rate | 10% |  | Status date | 2027-03-31
Category | Line Item | Qty | Unit | Unit Cost ($) | Budget ($) | Actual to Date ($) | Variance ($) | % Spent
Labor | Project management | 9 | month | 14000 | 126000 | 70000 | 56000 | 55.56%
Labor | UX/UI design | 10 | week | 6500 | 65000 | 68250 | -3250 | 105%
Labor | Front-end development | 24 | week | 7200 | 172800 | 86400 | 86400 | 50%
Labor | Back-end & integrations | 20 | week | 7800 | 156000 | 70200 | 85800 | 45%
Labor | QA & testing | 12 | week | 5400 | 64800 | 0 | 64800 | 0%
Software & Licensing | Document SDK license | 1 | year | 45000 | 45000 | 45000 | 0 | 100%
Software & Licensing | Cloud hosting | 9 | month | 3200 | 28800 | 16000 | 12800 | 55.56%
Software & Licensing | Monitoring & logging | 9 | month | 450 | 4050 | 2250 | 1800 | 55.56%
Infrastructure | Staging environment | 1 | lot | 12000 | 12000 | 12000 | 0 | 100%
Infrastructure | Load testing service | 1 | lot | 6000 | 6000 | 0 | 6000 | 0%
Training & Change | Admin training sessions | 4 | session | 2500 | 10000 | 0 | 10000 | 0%
Training & Change | User guides & videos | 1 | lot | 8000 | 8000 | 0 | 8000 | 0%
Professional Services | Security audit | 1 | lot | 18000 | 18000 | 0 | 18000 | 0%
Professional Services | Accessibility review | 1 | lot | 7500 | 7500 | 0 | 7500 | 0%
Subtotal |  |  |  |  | 723950 | 370100 | 353850 | 51.12%
Contingency |  |  |  |  | 72395 |  | 72395
TOTAL PROJECT BUDGET |  |  |  |  | 796345 | 370100 | 426245 | 46.47%
BUDGET BY CATEGORY
Category | Budget ($) | Actual ($) | Variance ($) | % Spent
Labor | 584600 | 294850 | 289750 | 50.44%
Software & Licensing | 77850 | 63250 | 14600 | 81.25%
Infrastructure | 18000 | 12000 | 6000 | 66.67%
Training & Change | 18000 | 0 | 18000 | 0%
Professional Services | 25500 | 0 | 25500 | 0%
Total (before contingency) | 723950 | 370100 | 353850 | 51.12%
MONTHLY SPEND PLAN
Month | Phasing % | Planned ($) | Actual ($) | Cum. Planned ($) | Cum. Actual ($)
2026-11-01 | 6% | 43437 | 38500 | 43437 | 38500
2026-12-01 | 9% | 65155.5 | 61200 | 108592.5 | 99700
2027-01-01 | 14% | 101353 | 102400 | 209945.5 | 202100
2027-02-01 | 13% | 94113.5 | 79300 | 304059 | 281400
2027-03-01 | 13% | 94113.5 | 88700 | 398172.5 | 370100
2027-04-01 | 14% | 101353 |  | 499525.5
2027-05-01 | 13% | 94113.5 |  | 593639
2027-06-01 | 11% | 79634.5 |  | 673273.5
2027-07-01 | 7% | 50676.5 |  | 723950
Total | 100% | 723950 | 370100
Check: phasing = 100% and monthly actuals = line-item actuals |  |  |  | OK
Note on C5: Key assumption: contingency applied to the line-item subtotal. Edit to test recalculation.

## Timeline & Milestones
Timeline & Milestones
Project Alpha — phase schedule, progress, and key milestones
Status date |  | 2027-03-31
# | Phase | Owner | Start | End | Duration (days) | Working Days | % Complete | Status
1 | Discovery & Requirements | J. Lee | 2026-11-02 | 2026-11-27 | 26 | 20 | 100% | Complete
2 | UX/UI Design | M. Okafor | 2026-11-30 | 2027-01-22 | 54 | 40 | 95% | Overdue
3 | Front-end Build | S. Patel | 2027-01-04 | 2027-04-30 | 117 | 85 | 60% | In Progress
4 | Back-end & Integrations | R. Alvarez | 2027-01-11 | 2027-05-14 | 124 | 90 | 50% | In Progress
5 | QA & Security | K. Nguyen | 2027-04-05 | 2027-06-11 | 68 | 50 | 0% | Not Started
6 | Training & Rollout | D. Whitfield | 2027-06-01 | 2027-07-16 | 46 | 34 | 0% | Not Started
7 | Hypercare & Close | J. Lee | 2027-07-19 | 2027-07-30 | 12 | 10 | 0% | Not Started
Overall % complete (weighted by duration) | [6 empty] | 46.87%
KEY MILESTONES
# | Milestone | Phase | Due Date | Status | Days to Due
1 | Requirements sign-off | Discovery & Requirements | 2026-11-27 | Complete | 0
2 | Design approval | UX/UI Design | 2027-01-22 | Complete | 0
3 | Beta release | Front-end Build | 2027-04-30 | On Track | 30
4 | Integrations complete | Back-end & Integrations | 2027-05-14 | At Risk | 44
5 | Security audit passed | QA & Security | 2027-06-11 | Not Started | 72
6 | Go-live | Training & Rollout | 2027-07-16 | Not Started | 107
7 | Project close-out | Hypercare & Close | 2027-07-30 | Not Started | 121
Formulas:
Working Days = NETWORKDAYS(DATE(YEAR([Start]),MONTH([Start]),DAY([Start])),DATE(YEAR([End]),MONTH([End]),DAY([End])))

## Budget Scenarios
Budget Scenarios
What-if planning: change the blue inputs and the chart updates instantly
Scenario | Labor adjustment | Contingency | Labor ($) | Other costs ($) | Contingency ($) | Total ($)
Lean | -10% | 5% | 526140 | 139350 | 33274.5 | 698764.5
Base | 0% | 10% | 584600 | 139350 | 72395 | 796345
Expanded | 15% | 15% | 672290 | 139350 | 121746 | 933386
Labor and other costs come from the Cost Breakdown sheet. Nothing else in the workbook depends on this sheet.

## Dashboard
Project Alpha — Dashboard
Status as of March 31, 2027 · Health: At Risk
TOTAL BUDGET | SPENT TO DATE | OVERALL COMPLETE | MILESTONES DONE
796345 | 370100 | 46.87% | 2 of 7
incl. 10% contingency | 46.5% of budget | 1 overdue phase(s) | Next: Beta release